## Slide 1
STARTUPLAB BUSINESS CENTER
Fortune Procurement System
Meeting Recap — System Walkthrough & Demo
September 3, 2026 | 70-minute Zoom session
Prepared by Rovick Romasanta | StartupLab Business Center

## Slide 2
MEETING OVERVIEW
A live, end-to-end system walkthrough
The session demonstrated the full procurement workflow in real time — from item request through final goods receipt — with warehouse, operations, procurement, and director-level users each logging in and performing their actual step in the process.
MEETING TYPE
Impromptu Zoom — System Walkthrough / Demo
DATE
September 3, 2026
DURATION
70 minutes
ATTENDEES
StartupLab
Richard F. Prodigalidad
Rovick Romasanta
Client — Fortune Procurement
Judy and the Procurement Team
Marcial Amaro VI
FPC Training Room participants:
Warehouse, Operations, Director, and QA
Fortune Procurement System — Meeting Recap
02

## Slide 3
WORK DEMONSTRATED
The procurement cycle, step by step (1 of 2)
Request → Canvassing → PR2 Approval
1
Item request & validation
Available quantity and requested quantity fields captured at intake.
2
Warehouse quantity review & adjustment
Any change requires a documented reason.
3
Department head approval
Approval history and timestamps are visible.
4
Operations manager approval
5
RFQ creation & assignment
Assigned to a procurement staff member.
6
Supplier canvassing & invitation
Suppliers invited by item and supplier type.
7
Supplier quotation submission
Unit price, lead time, remarks, and attachments.
Fortune Procurement System — Meeting Recap
03

## Slide 4
WORK DEMONSTRATED
The procurement cycle, step by step (2 of 2)
Quotation Comparison → PO → Goods Receipt
8
Quotation comparison & winning-supplier selection
9
PR2 approval
Procurement manager and director sign-off.
10
Purchase order generation & submission
PO submitted for approval.
11
PO transmission & supplier acknowledgment
Commitment date and delivery remarks captured.
12
Delivery status tracking
Tracked through to “Delivered.”
13
Warehouse goods receipt (GRN)
Received quantity entry, optional QA forwarding, transaction close.
Fortune Procurement System — Meeting Recap
04

## Slide 5
DECISIONS CONFIRMED
Four decisions locked in during the session
✓
Quantity adjustment ownership
Warehouse — not the original requester — will adjust order quantities, since warehouse has visibility into stock on hand and reorder points. A reason is captured for every change.
✓
Inventory system integration
Not yet connected to the client’s existing inventory/ERP system. Warehouse will manually cross-check stock for now. A future sync (potentially AI-assisted) will be scoped as a separate project.
✓
Approval accountability
Every approval step records who approved it and the date/time, giving full traceability across the cycle.
✓
User access
All users — requesters, department heads, directors, and other roles — will be issued individual accounts scoped to department and position.
Fortune Procurement System — Meeting Recap
05

## Slide 6
OPEN ITEMS
Two items remain open for follow-up
OPEN-01
Last purchase / acquisition cost
Raised by Marcial Amaro VI
Whether the last acquisition cost for an item should be visible during quotation comparison. Not currently available — historical pricing has not been imported. Will be flagged as out of scope for now when explaining the dashboard to the relevant stakeholder.
OPEN-02
Inventory system linking
Follow-up after soft launch
How to connect the client’s current inventory/sales data to the dashboard. StartupLab will look into feasible options — direct extraction vs. other methods — once on site.
Fortune Procurement System — Meeting Recap
06

## Slide 7
ACTION ITEMS
Who owns what before the next session
CLIENT ACTIONS
Prepare and finalize the full list of Engineering department users for the pilot — name, email, department, and position — using StartupLab’s template.
Review this summary and confirm the pilot department assignments (Engineering as primary, with Purchasing and Stockroom also involved).
STARTUPLAB ACTIONS
Send the user-list Excel template to the client for completion.
Create user accounts and configure access levels by department and position once the list is received.
Prepare a 10–15 day implementation plan with an itemized list of requirements ahead of soft launch.
Send proposed implementation dates to Julie for scheduling.
Draft a short memorandum/announcement to the pilot team once dates are confirmed.
Fortune Procurement System — Meeting Recap
07

## Slide 8
NEXT STEPS
Path to go-live
Pilot departments: Engineering (primary), together with Purchasing and Stockroom.
1
Follow-up demo /
training
Held with the pilot team prior to go-live
2
Soft launch
Target: within the next weeks
3
Wide-scale
implementation
By end of month or early next month
Fortune Procurement System — Meeting Recap
08

## Slide 9
THANK YOU
On track for soft launch within 1–2 weeks.
Next up: pilot user list from Engineering, followed by a hands-on training session with the pilot team.
StartupLab Business Center
Prepared by Rovick Romasanta — Fortune Procurement System project